cÖKí mvims‡ÿc
1|
cÖK‡íi bvg
t
Coastal Embankment Improvement Project​ Phase 1



(programme in Satkhira, Khulna, Bagerhat, Pirojpur, Barguna and Patuakhali District)

2|
(K) gš¿Yvjq
t
cvwb m¤ú` gš¿Yvjq 


(L) ms¯’v
t
(1) evsjv‡`k cvwb Dbœqb †evW© (evcvD‡ev) 

3|
cÖK‡íi cUf~wg  t


2007 mv‡ji b‡f¤^i gv‡mi 15 ZvwiL N~wY©So ÒwmWiÓ evsjv‡`‡ki DcK~jeZx© GjvKvq cÖPÛ kw³‡Z AvNvZ nv‡b| N~wY©S‡o DcK~jeZx© 30wU †Rjv wewfbœ gvÎvq ¶wZMÖ¯— nq| Zb¥‡a¨ wc‡ivRcyi, ei¸bv, cUzqvLvjx I ev‡MinvU †Rjv me©vwaK ¶wZMÖ¯— nq| N~wY©S‡o cÖvq 3200 gvbyl gviv hvq| wmW‡ii ¶q¶wZi cwigvb wbiƒc‡bi wbwgË wek¦e¨vsK I Ab¨vb¨ Dbœqb mn‡hvMx ms¯’vi mgš^‡q †hŠ_ wgkb Joint Damage Loss and Needs Assessment (JDLNA) welqK GKwU Rwic cwiPvjbv K‡i| D³ ¶q¶wZ Rwi‡ci wfwË‡Z wek¦e¨vsK 6 A‡±vei 2008 Gi Project Paper- G N~wY©So wmW‡ii ¶q¶wZ cybe©vm‡bi Rb¨ evsjv‡`k miKvi‡K 109.00 wgwjqb gvwK©b Wjvi mnvqZv cÖ`v‡bi wbðqZv †`q| Dnvi Av‡jv‡K “Emergency 2007 Cyclone Recovery & Restoration Project (ECRRP)” kxl©K cÖKíwU MZ 23/10/2008 Zvwi‡L AbywôZ GK‡bK mfvq Aby‡gvw`Z nq|

ÒBwmAviAviwc-Gi wWwcwc-‡Z evsjv‡`‡ki DcK~jeZx© AÂjmg~‡ni mgMÖ †cvìvi¸‡jv‡K Rjevqyi µgea©gvb DòZvi Kvi‡Y m„ó N~wY©So, R‡jv”Qvm, mgy‡`ªi cvwbi D”PZv e„w× BZ¨vw`i Kej †_‡K i¶vK‡í “Technical Feasibility Studies and Detailed Design for Coastal Embankment Improvement Program (CEIP)” kxl©K mgx¶v ev¯Íevq‡bi j‡¶¨ cÖ‡qvRbxq A‡_©i ms¯’vb wQj| †m j‡ÿ¨ AvšÍR©vwZK civgk©K cÖwZôvb wb‡qv‡Mi gva¨‡g GB mgxÿv m¤úv`b Kiv nq| civgk©K cÖwZôvb KZ…©K m¤úvw`Z mgxÿv Kv‡Ri Av‡jv‡K wek¦ e¨vsK DcKzjxq AÂ‡j 17wU ‡cvìvi‡K Rjevqy cwieZ©b RwbZ m„ó NywY©So †gvKv‡ejv Dc‡hvMx K‡i mvwe©Kfv‡e evua mg~n‡K Dbœqb I cybe©vmb Kivi wbwgË 400.00 wgwjqb gvwK©b Wjvi A_© mnvqZvi cÖ`v‡b m¤§Z nq| GB Av‡jv‡K m¤ú~Y© wek¦ e¨vsK I wcwcwmAvi Aby`v‡b 3280.00 †KvwU UvKv e¨q m¤^wjZ “Coastal Embankment Improvement Project, Phase-I (CEIP-I)” kxl©K cÖK‡íi wWwcwc cÖYqb c~e©K cvwb m¤ú` gš¿Yvj‡q gva¨‡g cwiKíbv Kwgk‡b †cÖiY Kiv n‡j, MZ 01-10-13 Zvwi‡Li D³ wWwcwc-wU GK‡bK mfvq Aby‡gvw`Z nq| cvwb m¤ú` gš¿Yvjq n‡Z MZ 27-10-14 Zvwi‡L “Coastal Embankment Improvement Project, Phase-I (CEIP-I)” kxl©K cÖK‡íi cÖkvmwbK Av‡`k Rvix Kiv nq| GB cÖKí ev¯Íevq‡bi gva¨‡g DcKzjxq AÂ‡ji 6wU †Rjvi 17wU ‡cvìvi‡K Rjevqy cwieZ©b RwbZ m„ó NywY©So †gvKv‡ejv Dc‡hvMx K‡i mvwe©Kfv‡e evua mg~n‡K Dbœqb I cybe©vmb Kiv n‡e| d‡j DcKzjxq AÂj b`x M‡f© wejxb nIqv †_‡K iÿv cv‡e Ges cÖvK„wZK `y‡h©v‡Mi mgq km¨, cÖvwYm¤ú` I Ab¨vb¨ m¤ú‡`i ÿqÿwZ n«vm cv‡e|
4|
cÖK‡íi D‡Ïk¨ t

DcKzjxq AÂ‡ji †cvìvi mg~n‡K mvgMÖxKfv‡e cybe©vmb I Dbœq‡bi gva¨‡g wb¤œewY©Z D‡Ïk¨ AR©b Kiv
· cÖvK„wZK `y‡h©v‡Mi mgq km¨, cÖvwYm¤ú` Ges Ab¨vb¨ m¤ú‡`i ÿqÿwZ n«vm;

· N~wY©So I mvB‡K¬v‡bi gZ cÖvK„wZK `y‡h©v‡Mi mgq Recovery time Kwg‡q Avbv;

· Rjevqy cwieZ©bRwbZ Kvi‡Y N~wY©S‡oi mgq m„ô R‡jv”Qvm cÖwZ‡iva Kiv ÿgZv Dc‡hvMx evua DPzKi‡Yi gva¨‡g m¤ú‡`i ÿqÿwZ n«vm;
· Rjevqy cwieZ©bRwbZ Kvi‡Y jeYv³ cvwb AbycÖ‡ek †iv‡ai gva¨‡g km¨ Drcv`b e„w×; I
· Riæix cÖvK„wZK wech©‡qi †ÿ‡Î `ªæZ Ges Kvh©Kifv‡e e¨e¯’v MÖn‡Y evsjv‡`k miKv‡ii `ÿZv e„w×|
5|
cÖK‡íi DcKvwiZv t

· cÖvK„wZK `y‡h©v‡Mi mgq km¨, cÖvwYm¤ú` Ges Ab¨vb¨ m¤ú‡`i ÿqÿwZ n«vm cv‡e;

· Rjevqy cwieZ©bRwbZ Kvi‡Y jeYv³ cvwb AbycÖ‡ek †iv‡ai gva¨‡g km¨ Drcv`b e„w× cv‡e;

· Riæix cÖvK„wZK wech©‡qi †ÿ‡Î `ªæZ Ges Kvh©Kifv‡e e¨e¯’v MÖn‡Y evsjv‡`k miKv‡ii `ÿZv e„w× cv‡e;

· Rjevqy cwieZ©bRwbZ Kvi‡Y N~wY©S‡oi mgq m„ô R‡jv”Qvm cÖwZ‡iva Kiv ÿgZv Dc‡hvMx K‡i DcKzjxq AÂ‡ji evua mg~n‡K cybe©vmb I Dbœqb Kiv n‡e;

· 17 wU †cvìv‡ii 100,817 †nt GjvKv N~wY©S‡oi mgq m„ô R‡jv”Qvm RwbZ cøve‡bi nvZ n‡Z iÿv cv‡e;

· DcKzjxq AÂ‡ji 17 wU †cvìvi mg~‡ni evua I Avf¨šÍwib wb¯‹vkb e¨e¯’vi Dbœqb Ges †mP myweavi gva¨‡g 86,382 †nt GjvKvq km¨ Drcv`b e„w× cv‡e ;

· N~wY©So m„ô R‡jv”Qvm cÖwZ‡iva ÿgZv m¤úbœ euv‡ai Kvi‡Y D”P djbkxj km¨ Drcv`‡bi AvKl©Y e„w× n‡e;

· DcKzjxq AÂ‡ji gvby‡li (†gvU RbmsL¨vi GK-Z…Zxqvsk) Rb¨ RxweKvi cªmvi Ges RxebhvÎvi gv‡bvbœqb Z_v evsjv‡`‡ki Av_©-mvgvwRK Dbœqb mvab n‡e;

· my›`ie‡bi ebR m¤ú` I Rxe-‰ewPÎ¨ i¶v cv‡e;

· †`‡ki DËivÂ‡ji mv‡_ `wÿb-cwðgvÂ‡ji mivmwi †hvMv‡hvM I cwienb e¨e¯’vi Dbœqb n‡e|

6|
cÖKí GjvKv t 

	wbe©vPbx GjvKv
	wefvM
	‡Rjv
	Dc‡Rjv

	96 ev‡MinvU-2
	Lyjbv
	ev‡MinvU
	ev‡MinvU m`i

	97 ev‡MinvU-3
	Lyjbv
	ev‡MinvU
	ivgcvj

	98 ev‡MinvU-4
	Lyjbv
	ev‡MinvU
	kiY‡Lvjv, †gv‡ojMÄ

	99 Lyjbv-1
	Lyjbv
	Lyjbv
	`v‡Kvc

	103 Lyjbv-5
	Lyjbv
	Lyjbv
	Wzgywiqv

	104 Lyjbv-6
	Lyjbv
	Lyjbv
	Kqiv, cvBKMvQv

	105 mvZÿxiv-1
	Lyjbv
	mvZÿxiv
	Zvjv

	108 mvZÿxiv-4
	Lyjbv
	mvZÿxiv
	k¨vgbMi

	109 ei¸bv-1
	ewikvj
	ei¸bv
	ei¸bv m`i

	110 ei¸bv-2
	ewikvj
	ei¸bv
	cv_iNvUv

	113 cUzqvLvjx-3
	ewikvj
	cUzqvLvjx
	MjvwPcv

	114 cUzqvLvjx-4
	ewikvj
	cUzqvLvjx
	Kjvcvov

	128 wc‡ivRcyi-2
	ewikvj
	wc‡ivRcyi
	fvÛvwiqv

	129 wc‡ivRcyi 3
	ewikvj
	wc‡ivRcyi
	gVevwoqv


7|
cÖK‡íi cÖv°wjZ e¨qt 

jÿ UvKvq
	wWwcwc
	Aby‡gv`‡bi ZvwiL
	wRIwe
	wcG
	‡gvU

	g~j
	27 A‡±vei 2013
	-
	328,000.00
	328,000.00

	AvšÍtLvZ mgš^q
	05 b‡f¤^i 2018
	-
	328,000.00
	328,000.00


8|
cÖK‡íi ev¯ÍevqbKvjt
	wWwcwc
	Avi¤¢
	mgvwß

	g~j
	RyjvB, 2013
	Ryb, 2020

	AvšÍtLvZ mgš^q
	RyjvB, 2013
	Ryb, 2020


9|
cÖK‡íi cÖavb A½mg~n t

jÿ UvKvq
	µwgK
	wWwcwc (AvšÍtLvZ mgb¦q)Abyhvqx cÖavb A½mg~n
	cwigvb
	cÖv°wjZ e¨q

	1|
	ivR¯^ e¨q
	
10
`dv
	58784.36

	2|
	hš¿cvwZ I hvbevnb µq
	
1
`dv
	1545.30

	3|
	ebvqb
	
1
`dv
	3280.00

	4|
	Rwg AwaM«nY
	
544.16
†nt
	45394.95

	5|
	evua wbg©vY/ c~bt wbg©vY 
	
624.80
wKtwgt
	53182.10

	6|
	wb¯‹vkb Lvj Lbb/c~btLbb 
	
485.29
wKtwgt
	6047.36

	7|
	cvwb wb¯‹vkb AeKvVv‡gv wbg©vY 
	
124
wU
	29012.39

	8|
	cvwb wb¯‹vkb AeKvVv‡gv †givgZ 
	
14
wU
	590.54

	9|
	d¬vwks Bb‡jU wbg©vY 
	
158
wU
	16894.48

	10|
	d¬vwks Bb‡jU †givgZ
	
52
wU
	1373.04

	11|
	euv‡ai Xvj cÖwZiÿv KvR 
	
52.90
wKtwgt
	27923.75

	12|
	b`x Zxi msiÿY KvR 
	
22.05
wKtwgt
	54814.61

	13|
	‡K¬vRvi wbg©vY 
	
9
wU
	2840.49

	14|
	Ab¨vb¨ g~jabx e¨q
	
1
`dv
	13643.40

	15|
	Ab¨vb¨ (wdwRK¨vj I cÖvBR KbwU‡RwÝ)
	
1
`dv
	12673.23

	
	 ‡gvU 
	
	328,000.00


10|
cÖK‡íi µgcyÄxf~Z AMÖMwZ t

jÿ UvKvq

	mgqKvj
	wRIwe
	cÖKí mvnvh¨
	 †gvU Avw_©K
	ev¯Íe (%)

	Ryb, 2018
	0.00
	76597.85
	76597.85
	23.35

	Rvbyqvwi, 2019
	0.00
	83396.37
	83396.37
	25.44

	AMÖMwZ
	0.00
	6798.52
	6798.52
	2.09


11|  Aby‡gvw`Z AvšÍtLvZ mgš^q wWwcwc  Abyhvqx eQi Iqvix eivÏ I cÖvß eivÏ t                             j¶ UvKvq
	A_© eQi
	wWwcwc (AvšÍtLvZ mgš^q) Abyhvqx 
	cÖvß eivÏ

	2013-2014
	360.05
	540.00

	2014-2015
	2000.00
	2000.00

	2015-2016
	14991.66
	25000.00

	2016-2017
	22496.27
	40000.00

	2017-2018
	36750.59
	40000.00

	2018-2019
	80000.00
	80000.00

	2019-2020
	171401.43
	

	‡gvU
	328,000.00
	187,540.00


12|
cÖK‡íi ev¯Íevqb mgm¨v 
t 
· cÖK‡íi †fŠZ Kv‡Ri 03 wU c¨v‡K‡Ri g‡a¨ 02 wU c¨v‡K‡Ri (c¨v‡KR-1 I c¨v‡KR-2) ev¯Íevqb KvR Pj‡Q| Rwg AwaMÖnY Kv‡R e¨q e„w×i Kvi‡Y c¨v‡KR-3 ev¯Íevq‡bi cÖ‡qvRbxq A‡_©i msKyjvb bv nIqvq `icÎ Avnevb Kiv hv‡PQ bv|
· c¨v‡KR-2 Gi f~wg AwaMÖn‡Y wej¤^ nIqvq KvR ev¯Íevq‡b weNœ NU‡Q| G‡Z wba©vwiZ mg‡qi (RybÕ 2020 Bs) g‡a¨ cÖKí ev¯Íevqb m¤fe n‡e bv|
· b`xi gidjwRK¨vj cwieZ©‡bi Kvi‡Y †cvìvi mg~‡ni wewfbœ As‡k bZzbfv‡e fv΅b †`Lv †`Iqvq AwZwi³ b`x Zxi msiÿY Kv‡Ri cÖ‡qvRbxqZv †`Lv w`‡q‡Q| G‡Z cÖvq AwZwi³ 1500.00 †KvwU UvKvi cÖ‡qvRb n‡e|
13|
m¤¢ve¨ mgvavb  
t 
·  wek^ e¨vsK AwZwi³ b`x Zxi msiÿY KvRmn c¨v‡KR-3 ev¯Íevq‡bi cÖ‡qvRbxq AwZwi³ A‡_©i       ms¯’v‡b m¤§Z n‡j cÖKí ev¯Íevq‡bi cÖ‡qvRbxq AwZwi³ A_© eiv‡×i Rb¨ wWwcwc ms‡kvab Ki‡Z   n‡e| 
· ms‡kvwaZ wWwcwc‡Z cÖK‡íi mgq `yB eQi e„w× Ki‡Z n‡e|

[image: image1]
[image: image2.jpg]WEST BENGAL
(INDIX)





`wÿb-cwðgvÂjxq DcKyjxq GjvKvq ev¯ÍevwqZ †cvìvi

wmBAvBwc cÖKí GjvKv








332
73-8 Coastal Embankment Improvement Project​ Phase 1
333
73-8 Coastal Embankment Improvement Project​ Phase 1

[image: image3.png]LAKSHMIPUR
°

2450

BARISAL
JHALOKATI
L]

2150

Legend

I oetailed Design (5 nos)

Il Fessiviity Level Design (12 nos) % \ 7. 200N
[ | Completed sV N

[ ongaing 3

Not implemented
Under ECRRP Program

(Gontal Embankment Improvement Programme (EIP) Bay of Bengal

conutc s senves e v L. ek
N S




